## Project Timeline
Task ID | Activity | Start Day | End Day | Duration | Status
T001 | Project Kick-off | 1 | 1 | 1 | Completed
T002 | Venue Confirmation | 2 | 3 | 2 | Completed
T003 | Budget Preparation | 4 | 6 | 3 | Completed
T004 | Vendor Identification | 5 | 8 | 4 | Completed
T005 | Sponsor Coordination | 8 | 10 | 3 | Completed
T006 | Vendor Finalization | 11 | 15 | 5 | Completed
T007 | Security Planning | 15 | 18 | 4 | Completed
T008 | Branding Preparation | 18 | 20 | 3 | Completed
T009 | Volunteer Recruitment | 21 | 25 | 5 | Completed
T010 | Ticketing Setup | 22 | 26 | 5 | Completed
T011 | Logistics Planning | 25 | 28 | 4 | Completed
T012 | Technical Preparation | 28 | 30 | 3 | Completed
T013 | Venue Inspection | 31 | 35 | 5 | Completed
T014 | Staff Training | 32 | 36 | 5 | Completed
T015 | Vendor Review Meeting | 35 | 38 | 4 | Completed
T016 | Venue Setup | 38 | 40 | 3 | Completed
T017 | Technical Installation | 41 | 42 | 2 | Completed
T018 | Food Court Setup | 42 | 42 | 1 | Completed
T019 | Full Rehearsal | 43 | 43 | 1 | Completed
T020 | Final Inspection | 44 | 44 | 1 | Completed
T021 | Match Day | 45 | 45 | 1 | Completed
T022 | Venue Cleanup | 46 | 46 | 1 | Completed
T023 | Post Event Review | 47 | 47 | 1 | Completed

## Gantt Chart
Task ID | Activity | Start Day | End Day | Duration | Day 1 | Day 2 | Day3 | Day 4 | Day 5 | Day 6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14 | Day15 | Day16 | Day17 | Day18 | Day19 | Day20 | Day21 | Day22 | Day23 | Day24 | Day25 | Day26 | Day27 | Day28 | Day29 | Day30 | Day31 | Day32 | Day33 | Day34 | Day35 | Day36 | Day37 | Day38 | Day39 | Day40 | Day41 | Day42 | Day43 | Day44 | Day45 | Day46 | Day47
T001 | Project Kick-off | 1 | 1 | 1
T002 | Venue Confirmation | 2 | 3 | 2
T003 | Budget Preparation | 4 | 6 | 3
T004 | Vendor Identification | 5 | 8 | 4
T005 | Sponsor Coordination | 8 | 10 | 3
T006 | Vendor Finalization | 11 | 15 | 5
T007 | Security Planning | 15 | 18 | 4
T008 | Branding Preparation | 18 | 20 | 3
T009 | Volunteer Recruitment | 21 | 25 | 5
T010 | Ticketing Setup | 22 | 26 | 5
T011 | Logistics Planning | 25 | 28 | 4
T012 | Technical Preparation | 28 | 30 | 3
T013 | Venue Inspection | 31 | 35 | 5
T014 | Staff Training | 32 | 36 | 5
T015 | Vendor Review Meeting | 35 | 38 | 4
T016 | Venue Setup | 38 | 40 | 3
T017 | Technical Installation | 41 | 42 | 2
T018 | Food Court Setup | 42 | 42 | 1
T019 | Full Rehearsal | 43 | 43 | 1
T020 | Final Inspection | 44 | 44 | 1
T021 | Match Day | 45 | 45 | 1
T022 | Venue Cleanup | 46 | 46 | 1
T023 | Post Event Review | 47 | 47 | 1

## Dashboard
Project Timeline Dashboard
KPI | Value
Total Activities | 23
Planning Duration | 47 Days
Milestones | 9
Project Status | Completed
Metric | Value
Total Tasks | 23
Project Duration | 47 Days
Match Day | Day 45
Completion | Day 47
Current Status | Completed
Status | Count
Completed | 23
Note: This project timeline represents the planned schedule for the Pro Kabaddi Hyderabad Event Management portfolio case study. Dates and activities are illustrative for educational purposes